## Roadmap
ECOMMERCE WEBSITE — SPRINT ROADMAP
Deadline | 31-Mar-2027 | Cadence | 2-week sprints | Release model | Single-store launch | Capacity warning | Team capacity must be confirmed in S1
Sprint | Sprint name | Start | End | Goal | Rollout / main features | Exit criteria | Capacity note | Dependencies
S1 | Discovery & Foundations | 2026-10-26 | 2026-11-06 | Turn the product brief into an agreed delivery baseline; establish architecture, engineering standards, environments, and core UX direction. | Requirements baseline; architecture and service boundaries; repo/branch strategy; CI checks; dev environment; data model draft; design tokens and wireframes; threat model; definition of ready/done. | PRD and backlog reviewed; core ADRs approved; code builds in CI; dev environment reproducible; initial wireframes reviewed; priority decisions have owners and due dates. | Normal | Kickoff; named product owner; engineer/QA/design availability.
S2 | Platform Shell & Identity | 2026-11-09 | 2026-11-20 | Create the working application shell, shared UI/API foundations, and secure customer identity flows. | Next.js app shell; responsive design system; Express service skeletons; auth/register/login/logout/refresh; profile/address foundation; RBAC; Zod validation; standard API/error response; basic audit events. | Identity APIs tested; auth/session design reviewed; protected routes and role checks work; shared form controls meet initial accessibility checks; CI test gates run. | Normal | S1 architecture and UX foundation.
S3 | Catalog & Discovery | 2026-11-23 | 2026-12-04 | Make customers able to browse and discover active products through category pages, search, sorting, and filters. | Category hierarchy; product model and variants; listing pages; pagination; keyword search; sort/filter; availability and price display; catalog API; admin product CRUD v1; seed/import tooling. | Catalog endpoints and UI have integration tests; filters/sort/pagination produce consistent results; unpublished products stay hidden from customers; seed data supports end-to-end test. | Normal | S2 API, auth, shared components.
S4 | Product Detail & Inventory | 2026-12-07 | 2026-12-18 | Complete the product evaluation experience and establish stock and media handling. | Product detail page; image gallery; variants/SKUs; stock availability; SKU and inventory admin; S3 image upload; CDN delivery; SEO metadata; related products v1; product schema validation. | Variant selection updates price/availability; out-of-stock cannot be purchased; image upload validates size/type; product pages render metadata and canonical URLs. | Normal | S3 catalog/product model; AWS storage baseline.
S5 | Cart, Wishlist & Offers | 2026-12-21 | 2027-01-01 | Build the saved shopping state and initial promotion rules while planning reduced holiday capacity. | Guest and authenticated cart; merge cart on login; quantity edits; remove/save for later; wishlist; subtotal/discount estimate; coupon creation and validation; pricing calculation service; cart persistence. | Cart survives refresh/login; quantity and stock constraints enforced server-side; coupon eligibility/limits validated on backend; price totals are calculated server-side; holiday capacity adjusted. | Reduced (holiday period) | S3/S4 product and inventory APIs; S2 identity.
S6 | Checkout & Payment Integration | 2027-01-04 | 2027-01-15 | Create a secure checkout pipeline for addresses, delivery options, final pricing, and payment initiation. | Address book and checkout address; shipping options/rules; tax calculation integration or approved rules; order review; inventory reservation; payment provider sandbox; idempotent checkout initiation; failure/retry states; consent and policy links. | A valid cart can reach payment sandbox; no payment card data stored by platform; totals revalidated server-side; duplicate clicks do not create duplicate orders/payments; decline/cancel paths tested. | Normal | S5 pricing/cart; S1 decisions on market, tax, currency, payment/shipping providers.
S7 | Orders & Payment Reconciliation | 2027-01-18 | 2027-01-29 | Complete order creation, verified payment status, customer order visibility, and transactional notifications. | Payment webhooks/signature verification; order/payment state machine; order detail/history; confirmation email; invoice/receipt baseline; transactional outbox or retryable jobs; order status timeline; reconciliation logs. | Order state is driven by verified provider events; webhook replay is idempotent; customer sees correct status; payment failures/refunds do not mark an order paid; notification failures retry safely. | Normal | S6 checkout and provider sandbox; email provider credentials.
S8 | Admin & Operations | 2027-02-01 | 2027-02-12 | Enable staff to operate the store without direct database edits. | Admin dashboard; role-gated catalog CRUD; bulk product import/export; inventory adjustments and audit trail; order search/detail; fulfilment/status updates; coupon management; customer lookup with restricted access; operational filters. | Only authorized roles can use admin actions; every sensitive stock/order adjustment is audited; invalid transitions are blocked; CSV import reports row-level errors; staff runbooks drafted. | Normal | S2 RBAC; S3/S4 catalog/inventory; S5 offers; S7 orders.
S9 | Retention, Reviews & Self-Service | 2027-02-15 | 2027-02-26 | Finish the agreed launch scope around post-purchase self-service, reviews, search quality, and notifications. | Product ratings/reviews with moderation; cancellation eligibility; return/refund request workflow per approved policy; email templates and preferences; search relevance tuning; wishlist; customer order self-service; accessibility/SEO gap closure; support contact path. | Return/cancel rules match approved policy; reviews are tied to eligible orders or clearly configured policy; email content and preference behavior tested; all P0 user journeys pass E2E tests. | Normal | S7 order lifecycle; PM approval for cancellation/return/review policies.
S10 | System Hardening & Release Candidate | 2027-03-01 | 2027-03-12 | Stabilize cross-service behavior and prove security, performance, accessibility, observability, and production deployment paths. | Full regression; contract/integration/E2E tests; performance baseline/load test; OWASP review; dependency/container scanning; WCAG audit; SEO crawl; structured logs/traces/alerts; backup restore test; CI/CD deployment to staging and prod; feature flags. | No open blocker/critical defects; agreed performance gates pass; security findings triaged with no unresolved critical/high blockers; backup restore and rollback rehearsed; go-live checklist reviewed. | Normal | Feature-complete S9; production AWS environment and secrets; test data.
S11 | UAT, Cutover & Launch Readiness | 2027-03-15 | 2027-03-26 | Complete business UAT, resolve launch blockers, validate operations, and approve the production release. | Business UAT; defect fixes; migration rehearsal; production smoke tests; payment live-mode validation; inventory opening load; customer support/runbooks; incident and rollback rehearsal; analytics verification; final accessibility/performance checks. | Product owner signs off against acceptance criteria; all P0 tests pass; no Sev-1/Sev-2 defects open; monitoring/alerts active; business operations ready; release go/no-go signed. | Normal; protect from scope growth | S10 RC; final content/policies/product data; provider production approvals.
R | Production Launch Window | 2027-03-29 | 2027-03-31 | Deploy the approved release, monitor live traffic, and resolve launch-day issues. | Controlled deployment; smoke test; payment/order verification; availability and error monitoring; rapid rollback path; launch-day communications; daily triage. | Production smoke tests pass; a test order is completed and reconciled; no critical incident; support/monitoring staffed; release notes and known issues published. | Release window only | S11 signed go/no-go; production credentials; runbook and rollback verified.

## Ticket Backlog
TICKET-LEVEL DELIVERY BACKLOG
Ticket ID | Sprint | Epic | Title | Description / Scope | Acceptance Criteria | Priority | Owner Role | Story Points | Dependencies | Status | Notes | PRD Requirement IDs / Traceability
ECOM-001 | S1 | Governance | Confirm launch assumptions and decisions | Record launch market, currency, product ownership model, payment provider, shipping/tax approach, return/cancellation policy, review rules, expected traffic, and team capacity. | Each decision has an owner, due date, chosen option or explicit TBD, and impact if late. | P0 | PM / Product | 3 | None | Not Started | Refine with PM; add implementation subtasks and test evidence. | Scope; Architecture; NFRs
ECOM-002 | S1 | Requirements | Approve PRD and release scope | Review launch P0 scope, exclusions, success metrics, and release gates with product, engineering, design, QA, and operations. | Named approvers sign off; scope changes require impact review. | P0 | PM / Product | 3 | None | Not Started | Refine with PM; add implementation subtasks and test evidence. | Scope; Architecture; NFRs
ECOM-003 | S1 | Architecture | Create system context and service-boundary ADR | Define catalog, identity, cart, checkout/order, payment adapter, notification and admin boundaries; document synchronous vs asynchronous paths. | ADR lists APIs/events, data ownership, failure modes, and deployment approach. | P0 | Architect / Backend | 5 | None | Not Started | Refine with PM; add implementation subtasks and test evidence. | Scope; Architecture; NFRs
ECOM-004 | S1 | Engineering Platform | Create repositories and branch/PR conventions | Set up frontend, backend service packages or repos, linting, formatting, commit checks, code ownership, and PR template. | A fresh clone can run documented commands; main branch requires CI and review. | P0 | DevEx | 3 | None | Not Started | Refine with PM; add implementation subtasks and test evidence. | Scope; Architecture; NFRs
ECOM-005 | S1 | Engineering Platform | Build CI baseline | Add type checks, lint, unit-test job, dependency audit, and build checks for frontend and backend. | PR checks report pass/fail and block merges on configured required gates. | P0 | DevEx | 5 | None | Not Started | Refine with PM; add implementation subtasks and test evidence. | Scope; Architecture; NFRs
ECOM-006 | S1 | Cloud Platform | Provision development and staging skeleton on AWS | Define infrastructure as code, environment separation, network boundaries, least-privilege roles, and secret handling. | Dev and staging resources are reproducible; no secrets committed to source. | P0 | Cloud / DevOps | 5 | None | Not Started | Refine with PM; add implementation subtasks and test evidence. | Scope; Architecture; NFRs
ECOM-007 | S1 | Data | Draft ERD and migration conventions | Design initial entities and ownership; define migrations, IDs, timestamps, soft delete policy, and audit needs. | ERD reviewed; migration applies forward on clean database and is covered by test. | P0 | Backend / Data | 5 | None | Not Started | Refine with PM; add implementation subtasks and test evidence. | Scope; Architecture; NFRs
ECOM-008 | S1 | UX | Create responsive journey wireframes | Wireframe browse, product detail, cart, checkout, auth, order history, and admin core flows. | Product reviews desktop/mobile flows and error/empty/loading states. | P0 | UX / Product | 5 | None | Not Started | Refine with PM; add implementation subtasks and test evidence. | Scope; Architecture; NFRs
ECOM-009 | S1 | Security | Create threat model and security baseline | Identify risks around auth/session, payment/webhooks, admin privilege, PII, injection, abuse, and supply chain. | Risk register has mitigation, severity, owner, and verification method. | P0 | Security / Backend | 3 | None | Not Started | Refine with PM; add implementation subtasks and test evidence. | NFR-Security
ECOM-010 | S1 | Quality | Set Definition of Ready/Done and test strategy | Define ticket acceptance format, required automated coverage, environments, test data, and severity levels. | Team publishes shared DoR/DoD; P0 stories require acceptance tests and observability notes. | P0 | QA / PM | 2 | None | Not Started | Refine with PM; add implementation subtasks and test evidence. | NFR-Testing; Release Gates
ECOM-011 | S2 | Frontend Platform | Implement Next.js app shell and routing | Build global layout, navigation, footer, loading/error/not-found pages, responsive breakpoints, and route structure. | Core routes render at mobile/tablet/desktop; errors and loading states are consistent. | P0 | Frontend | 5 | S1 UX wireframes | Not Started | Refine with PM; add implementation subtasks and test evidence. | PLAT-02; UX / Accessibility
ECOM-012 | S2 | Design System | Build accessible reusable UI components | Implement button, input, select, checkbox, dialog, toast, skeleton, pagination, form field, badge, and modal patterns. | Keyboard behavior, visible focus, labels, error messaging and disabled states tested. | P0 | Frontend / UX | 5 | None | Not Started | Refine with PM; add implementation subtasks and test evidence. | PLAT-02; UX / Accessibility
ECOM-013 | S2 | Backend Platform | Create Express service template and API standards | Add TypeScript, config validation, health/readiness endpoints, request IDs, structured errors, logging, and graceful shutdown. | Service passes health checks; responses follow API envelope and errors do not leak internals. | P0 | Backend | 5 | S1 ADR | Not Started | Refine with PM; add implementation subtasks and test evidence. | PLAT-01–PLAT-06
ECOM-014 | S2 | Identity | Implement registration and email verification | Create account using validated fields; verify email with expiring single-use token; avoid account enumeration. | Duplicate email behavior is safe; invalid/expired token rejected; verification event recorded. | P0 | Backend / Frontend | 5 | None | Not Started | Refine with PM; add implementation subtasks and test evidence. | ID-01–ID-05; ID-08
ECOM-015 | S2 | Identity | Implement login, logout, refresh and session controls | Use short-lived access tokens and rotated, hashed refresh tokens in secure HttpOnly cookies or approved session strategy. | Refresh rotation/reuse detection and logout invalidation work; CSRF protections documented where cookie-based. | P0 | Backend / Security | 8 | S1 security ADR | Not Started | Refine with PM; add implementation subtasks and test evidence. | ID-01–ID-05; ID-08
ECOM-016 | S2 | Identity | Implement password reset and password policy | Issue one-time expiring reset token; apply agreed password policy and rate limits. | Token is single-use; reset invalidates previous sessions as specified; responses do not disclose account existence. | P0 | Backend | 5 | Registration/login | Not Started | Refine with PM; add implementation subtasks and test evidence. | ID-01–ID-05; ID-08
ECOM-017 | S2 | Authorization | Implement RBAC middleware and route policy | Define customer, support, catalog manager, fulfilment operator, and admin roles with server-side authorization. | Unauthorized requests return 401/403 appropriately; tests cover privilege escalation attempts. | P0 | Backend / Security | 5 | None | Not Started | Refine with PM; add implementation subtasks and test evidence. | ID-07
ECOM-018 | S2 | Validation | Standardize Zod request validation and API errors | Create shared schemas, request parsing, error codes, validation response structure and safe messages. | Invalid payloads return stable 400 errors with field details; no unhandled validation exceptions. | P0 | Backend | 3 | None | Not Started | Refine with PM; add implementation subtasks and test evidence. | PLAT-03
ECOM-019 | S2 | Profile | Create customer profile and address endpoints foundation | Add profile read/update and address CRUD scaffolding with ownership checks. | A user can only access their own profile/addresses; invalid fields rejected. | P0 | Backend | 3 | None | Not Started | Refine with PM; add implementation subtasks and test evidence. | ID-06; CHK-01
ECOM-020 | S3 | Catalog | Implement category hierarchy and navigation API | Support active categories, parent-child hierarchy, slug, order, and visibility. | Hidden/inactive categories are excluded from customer APIs; cycles and invalid parents prevented. | P0 | Backend | 5 | S1 ERD | Not Started | Refine with PM; add implementation subtasks and test evidence. | CAT-01–CAT-04
ECOM-021 | S3 | Catalog | Implement product/catalog schema and migrations | Support title, slug, description, SKU variants, price, compare-at price, category, attributes, status, media, and SEO metadata. | Constraints protect unique SKU/slug and valid price; migration and seed tests pass. | P0 | Backend / Data | 5 | None | Not Started | Refine with PM; add implementation subtasks and test evidence. | CAT-01–CAT-04
ECOM-022 | S3 | Catalog | Implement product listing API with pagination and sorting | Return published products with stable ordering and page/limit or cursor strategy. | Pagination metadata consistent; invalid sorts are rejected; unpublished products never leak. | P0 | Backend | 5 | None | Not Started | Refine with PM; add implementation subtasks and test evidence. | CAT-01–CAT-04
ECOM-023 | S3 | Discovery | Implement keyword search and filters v1 | Support product name/description keyword, category, price range, availability, and sort. | Combined filters behave predictably; empty result state and invalid ranges covered. | P0 | Backend | 5 | None | Not Started | Refine with PM; add implementation subtasks and test evidence. | CAT-07
ECOM-024 | S3 | Frontend Catalog | Build category, listing, sort and filter UI | Connect listing routes to APIs and maintain shareable filter state in URL. | Refresh/back/forward preserves filter state; mobile filters remain usable; loading/empty/error states exist. | P0 | Frontend | 8 | None | Not Started | Refine with PM; add implementation subtasks and test evidence. | CAT-01–CAT-04
ECOM-025 | S3 | Admin Catalog | Implement admin product CRUD v1 | Provide role-gated create/update/archive product flows and field validation. | Only catalog roles can edit; required fields enforced; product status controls customer visibility. | P0 | Full-stack | 8 | S2 RBAC | Not Started | Refine with PM; add implementation subtasks and test evidence. | CAT-02; ADM-02
ECOM-026 | S3 | Content | Create seed data and local catalog fixtures | Create realistic non-production products/categories/images to support demos and repeatable tests. | Seed is idempotent and never loads demo data into production by default. | P0 | Backend / QA | 3 | None | Not Started | Refine with PM; add implementation subtasks and test evidence. | CNT-01
ECOM-027 | S4 | Product Detail | Build product detail page and variant selector | Display imagery, description, attributes, price, availability, variant/SKU and quantity. | Changing variant updates price/SKU/stock; unavailable variants cannot be added to cart. | P0 | Frontend | 8 | S3 catalog API | Not Started | Refine with PM; add implementation subtasks and test evidence. | CAT-05
ECOM-028 | S4 | Media | Implement secure product media upload | Use pre-signed S3 uploads or approved upload service, validate type/size, and serve via CDN. | Only authorized staff upload; unsupported files rejected; assets are not publicly writable. | P0 | Backend / Cloud | 5 | None | Not Started | Refine with PM; add implementation subtasks and test evidence. | CAT-06
ECOM-029 | S4 | Inventory | Implement inventory read and adjustment model | Track available/reserved/committed stock by SKU; restrict adjustments to authorized roles. | Stock cannot become negative through normal operations; adjustments are auditable. | P0 | Backend / Data | 8 | None | Not Started | Refine with PM; add implementation subtasks and test evidence. | ADM-03; CHK-05
ECOM-030 | S4 | Admin Inventory | Build SKU/stock admin UI | Allow inventory lookup, adjustment reason, and low-stock view. | Unauthorized roles blocked; adjustment includes actor, timestamp, reason, and SKU. | P0 | Full-stack | 5 | Inventory API | Not Started | Refine with PM; add implementation subtasks and test evidence. | ADM-03; CHK-05
ECOM-031 | S4 | SEO | Implement product/category metadata and canonical links | Generate title, description, canonical URLs, robots directives and product structured data where appropriate. | Published product pages have unique metadata; hidden/draft pages are not indexable. | P0 | Frontend | 5 | None | Not Started | Refine with PM; add implementation subtasks and test evidence. | CAT-08; NFR-SEO
ECOM-032 | S4 | Recommendations | Add related products v1 | Show curated or same-category items without blocking primary product rendering. | Missing recommendations gracefully hide the module; no broken product links. | P1 | Frontend / Backend | 3 | None | Not Started | Refine with PM; add implementation subtasks and test evidence. | CAT-09
ECOM-033 | S5 | Cart | Implement persistent guest and customer cart | Support add/update/remove cart line items and persistence; merge guest cart on login. | Server recalculates product prices/availability; duplicate lines are consolidated; merge conflicts have deterministic rules. | P0 | Backend | 8 | S3/S4 catalog and inventory | Not Started | Refine with PM; add implementation subtasks and test evidence. | CART-01–CART-04
ECOM-034 | S5 | Cart UI | Build cart drawer/page and quantity controls | Show line items, stock messages, subtotal, savings and empty/error states. | Every mutation updates server state; quantity cannot exceed allowed stock; screen-reader status is announced. | P0 | Frontend | 5 | None | Not Started | Refine with PM; add implementation subtasks and test evidence. | CART-01–CART-04
ECOM-035 | S5 | Wishlist | Implement customer wishlist | Add/remove product or variant to wishlist; allow moving available item to cart. | Wishlist is private to customer; unavailable products remain clear and cannot be purchased. | P1 | Full-stack | 5 | S2 identity | Not Started | Refine with PM; add implementation subtasks and test evidence. | CART-06
ECOM-036 | S5 | Pricing | Create centralized pricing calculation module | Calculate line totals, subtotal, discounts and final amount with integer minor-unit money representation. | No client-supplied amount is trusted; rounding and currency precision rules are documented and tested. | P0 | Backend | 8 | None | Not Started | Refine with PM; add implementation subtasks and test evidence. | CART-03
ECOM-037 | S5 | Promotions | Implement coupon model and validation | Support fixed/percentage discount, active dates, usage limit, minimum basket, product/category eligibility and one-code policy. | Expired/ineligible/exhausted coupons fail safely; concurrency does not exceed usage limits. | P0 | Backend | 5 | None | Not Started | Refine with PM; add implementation subtasks and test evidence. | CART-05; ADM-04
ECOM-038 | S5 | UX | Create coupon apply/remove and totals summary UI | Allow entering a coupon and explain success/failure without losing cart state. | Totals match backend response; failures are actionable and not misleading. | P0 | Frontend | 3 | None | Not Started | Refine with PM; add implementation subtasks and test evidence. | Scope; Architecture; NFRs
ECOM-039 | S6 | Checkout | Build address book and checkout address selection | Allow selecting/adding/editing address during checkout with field validation. | Checkout verifies address completeness; address ownership enforced; validation errors are inline. | P0 | Full-stack | 5 | S2 profile/address | Not Started | Refine with PM; add implementation subtasks and test evidence. | ID-06; CHK-01
ECOM-040 | S6 | Checkout | Implement shipping options and delivery estimates | Implement launch-region shipping methods, eligibility, cost, and estimate from approved rules/provider. | Unavailable destinations are blocked with explanation; shipping total appears in final order amount. | P0 | Backend | 5 | S1 shipping decision | Not Started | Refine with PM; add implementation subtasks and test evidence. | CHK-01–CHK-07
ECOM-041 | S6 | Tax | Implement tax calculation adapter | Integrate approved tax provider or encode approved launch-market rules behind a replaceable adapter. | Tax calculation inputs/outputs recorded; totals are revalidated server-side; no silent fallback changes tax. | P0 | Backend | 5 | S1 market/tax decision | Not Started | Refine with PM; add implementation subtasks and test evidence. | CHK-03
ECOM-042 | S6 | Checkout | Implement checkout summary and final price validation | Create order preview with items, address, shipping, tax, discounts, and final amount. | Any stale price/stock change requires confirmation before payment; server is source of truth. | P0 | Backend / Frontend | 8 | Cart/pricing/shipping/tax | Not Started | Refine with PM; add implementation subtasks and test evidence. | CHK-01–CHK-07
ECOM-043 | S6 | Inventory | Implement stock reservation with expiry | Reserve stock while payment is pending and release reservations on timeout/failure/cancel. | Concurrent checkouts cannot oversell beyond policy; expired reservations are cleaned safely. | P0 | Backend / Data | 8 | S4 inventory | Not Started | Refine with PM; add implementation subtasks and test evidence. | ADM-03; CHK-05
ECOM-044 | S6 | Payments | Integrate payment provider sandbox adapter | Create payment intent/session and return a safe redirect/client token for the selected provider. | No raw card data touches app servers; sandbox success/decline/cancel scenarios work; secrets stay in secret manager. | P0 | Backend / Security | 8 | S1 provider decision | Not Started | Refine with PM; add implementation subtasks and test evidence. | PAY-01; PAY-02; PAY-04
ECOM-045 | S6 | Reliability | Add checkout idempotency keys | Require idempotency for order/payment creation and return the original result on safe retries. | Repeated request with same key does not create duplicate order or charge; key expiry/ownership defined. | P0 | Backend | 5 | Checkout/order model | Not Started | Refine with PM; add implementation subtasks and test evidence. | PLAT-04; PAY-02; PAY-04
ECOM-046 | S7 | Payments | Verify and process payment webhooks | Validate provider signatures, handle retries and event ordering, and persist provider event IDs. | Invalid signatures rejected; duplicate events are idempotent; handler responds quickly and retries safely. | P0 | Backend / Security | 8 | S6 payment adapter | Not Started | Refine with PM; add implementation subtasks and test evidence. | PAY-01; PAY-02; PAY-04
ECOM-047 | S7 | Orders | Implement order and payment state machines | Define allowed transitions for pending, paid, processing, fulfilled, delivered, cancelled, refunded and payment failure. | Only valid transitions accepted; state change is audited; payment/order state reconciliation is possible. | P0 | Backend | 8 | None | Not Started | Refine with PM; add implementation subtasks and test evidence. | ORD-01–ORD-06; PAY-03
ECOM-048 | S7 | Orders | Build order history and detail pages | Show order number, items, amount breakdown, address snapshot, status timeline and invoice/receipt link. | Customer can only view own orders; historical values do not change when catalog changes. | P0 | Full-stack | 8 | None | Not Started | Refine with PM; add implementation subtasks and test evidence. | ORD-01–ORD-06; PAY-03
ECOM-049 | S7 | Notifications | Send order confirmation emails | Use a transactional email provider and safe templates for order confirmation/payment status. | Emails are sent from reliable queue/job; failed sends retry; duplicate webhook does not duplicate confirmation. | P0 | Backend | 5 | None | Not Started | Refine with PM; add implementation subtasks and test evidence. | ORD-04; MSG-01; MSG-02
ECOM-050 | S7 | Documents | Generate basic invoice/receipt | Create downloadable order document using agreed legal/tax fields and immutable order snapshot. | Document matches paid order totals and does not expose internal IDs or other customers’ data. | P0 | Backend | 5 | S1 invoice/tax policy | Not Started | Refine with PM; add implementation subtasks and test evidence. | ORD-01–ORD-06; PAY-03
ECOM-051 | S7 | Reliability | Add asynchronous job retry and dead-letter handling | Implement queue/job policy for email, webhook follow-up and non-blocking tasks. | Retries are bounded with alerts; failed jobs are inspectable/replayable by authorized operators. | P0 | Backend / Cloud | 5 | None | Not Started | Refine with PM; add implementation subtasks and test evidence. | PLAT-04; PAY-02; PAY-04
ECOM-052 | S8 | Admin | Build role-aware admin dashboard | Provide operational landing page with counts, recent orders and low-stock signals. | Dashboard aggregates are permission-aware; no PII beyond role needs is displayed. | P0 | Frontend / Backend | 5 | None | Not Started | Refine with PM; add implementation subtasks and test evidence. | ADM-01–ADM-06
ECOM-053 | S8 | Admin Orders | Build order search and order detail operations | Find orders by order number, date, status and customer identifier; show payment and fulfilment timeline. | Search is permission-limited and audited; sensitive fields masked based on role. | P0 | Full-stack | 8 | S7 orders | Not Started | Refine with PM; add implementation subtasks and test evidence. | ORD-01–ORD-06; PAY-03
ECOM-054 | S8 | Fulfilment | Implement fulfilment status updates | Allow authorized operations users to mark packed/shipped/delivered and attach carrier/tracking number if supported. | State transitions follow policy; actor/time tracked; customer timeline updates. | P0 | Full-stack | 5 | None | Not Started | Refine with PM; add implementation subtasks and test evidence. | ORD-01–ORD-06; PAY-03
ECOM-055 | S8 | Admin Catalog | Add bulk catalog import/export | Support CSV template, preview/validation, row-level errors and safe exports. | Bad rows do not silently corrupt good data; imports require authorization and generate a summary. | P1 | Backend / Admin | 8 | None | Not Started | Refine with PM; add implementation subtasks and test evidence. | CAT-02; ADM-02
ECOM-056 | S8 | Promotions Admin | Build coupon administration UI | Allow authorized staff to create/edit/pause coupons and see usage. | Eligibility fields validated; usage constraints enforced server-side; changes are audited. | P0 | Full-stack | 5 | S5 coupons | Not Started | Refine with PM; add implementation subtasks and test evidence. | CART-05; ADM-04
ECOM-057 | S8 | Audit | Add admin action audit log UI/API | Record and search security-sensitive changes, inventory adjustments and order status updates. | Logs include actor/action/entity/time/correlation ID without secrets or unnecessary payment data. | P0 | Backend / Frontend | 5 | None | Not Started | Refine with PM; add implementation subtasks and test evidence. | ADM-06
ECOM-058 | S8 | Support | Create restricted customer lookup | Allow support role to locate customer/order for assistance without granting broad admin powers. | Support cannot change role, view passwords/payment secrets, or perform restricted refunds unless explicitly granted. | P1 | Full-stack / Security | 5 | None | Not Started | Refine with PM; add implementation subtasks and test evidence. | ADM-07
ECOM-059 | S9 | Reviews | Implement product reviews and ratings | Allow review submission under approved policy, rating aggregation, abuse throttling and moderation status. | Only eligible users can submit under configured rule; hidden/rejected reviews do not affect public average. | P1 | Full-stack | 8 | None | Not Started | Refine with PM; add implementation subtasks and test evidence. | REV-01
ECOM-060 | S9 | Returns | Implement cancellation eligibility and request flow | Apply cancellation rules by order status/time; create request and staff decision flow if approval is required. | Ineligible cancellations explain why; stock/payment side effects are consistent and audited. | P0 | Backend / Frontend | 8 | S7 state machine; policy decision | Not Started | Refine with PM; add implementation subtasks and test evidence. | RET-01–RET-03
ECOM-061 | S9 | Returns | Implement return/refund request workflow | Capture reason, items/quantities, evidence if needed, decision, refund request, and audit trail. | Refund cannot exceed captured amount; duplicate refunds blocked; gateway refund status reconciles with order. | P0 | Backend / Frontend | 8 | S1 return policy; S7 payment state | Not Started | Refine with PM; add implementation subtasks and test evidence. | RET-01–RET-03
ECOM-062 | S9 | Notifications | Finalize email templates and preference handling | Build templates for verification, reset, order, shipment, cancellation/refund and required notifications. | Templates render on mobile; marketing opt-in is separate from transactional messages; unsubscribe rules match policy. | P0 | Frontend / Backend | 5 | None | Not Started | Refine with PM; add implementation subtasks and test evidence. | ORD-04; MSG-01; MSG-02
ECOM-063 | S9 | Discovery | Tune search relevance and empty-state help | Improve ranking, typo tolerance if feasible, facets and zero-results suggestions within selected search approach. | Search quality reviewed against a small agreed query set; no-result state offers useful recovery. | P1 | Backend / Product | 5 | None | Not Started | Refine with PM; add implementation subtasks and test evidence. | CAT-07
ECOM-064 | S9 | Quality | Run end-to-end P0 journey suite | Automate register/login, browse, add to cart, coupon, checkout sandbox, order history, admin fulfilment, cancellation/refund happy and failure paths. | CI or scheduled staging suite runs consistently and stores artifacts; P0 flows have clear pass/fail. | P0 | QA / Full-stack | 8 | None | Not Started | Refine with PM; add implementation subtasks and test evidence. | NFR-Testing; Release Gates
ECOM-065 | S9 | Content | Add support/contact and policy pages | Create contact/help page and shipping, privacy, terms, refund, and cookie disclosures from approved content. | Legal/business copy approved; navigation links work; pages are responsive and discoverable. | P0 | Frontend / Product | 3 | None | Not Started | Refine with PM; add implementation subtasks and test evidence. | CNT-01
ECOM-066 | S10 | Quality | Execute full regression and contract testing | Validate service APIs, compatibility, migrations and cross-service workflows using controlled test fixtures. | No P0 regression; contract breaks fail CI; test evidence linked to release candidate. | P0 | QA / Backend | 8 | None | Not Started | Refine with PM; add implementation subtasks and test evidence. | NFR-Testing; Release Gates
ECOM-067 | S10 | Performance | Run load test and fix critical bottlenecks | Measure listing, product detail, cart and checkout under agreed traffic profile; tune queries/cache/CDN. | Agreed target profile and thresholds documented; no critical resource exhaustion; results and remediation recorded. | P0 | Performance / Backend | 8 | None | Not Started | Refine with PM; add implementation subtasks and test evidence. | NFR-Performance
ECOM-068 | S10 | Security | Run application security review | Check auth/session, access control, SSRF/injection, CSRF, XSS, secrets, dependencies, CORS, rate limits, webhooks and data exposure. | No unresolved critical/high issue without explicit risk acceptance; remediation retested. | P0 | Security / QA | 8 | None | Not Started | Refine with PM; add implementation subtasks and test evidence. | NFR-Security
ECOM-069 | S10 | Accessibility | Complete WCAG 2.2 AA-oriented audit | Keyboard/screen reader test key journeys; inspect focus, contrast, labels, error announcements and reduced motion. | No blocker on core checkout/accessibility paths; issues prioritized and retested. | P0 | UX / QA / Frontend | 5 | None | Not Started | Refine with PM; add implementation subtasks and test evidence. | NFR-Accessibility
ECOM-070 | S10 | SEO | Run technical SEO and crawl audit | Check indexability, canonical, sitemap, robots, metadata, structured data, redirects and duplicate URL handling. | Key public URLs crawl successfully; checkout/account/admin are noindex; broken canonical/robots issues fixed. | P0 | SEO / Frontend | 5 | None | Not Started | Refine with PM; add implementation subtasks and test evidence. | CAT-08; NFR-SEO
ECOM-071 | S10 | Observability | Add metrics, dashboards and alerts | Track request latency/error rate, service health, checkout failures, payment webhook lag, queue depth and DB saturation. | Alerts route to named on-call channel; runbook links included; logs have correlation IDs and redact PII. | P0 | Cloud / Backend | 8 | None | Not Started | Refine with PM; add implementation subtasks and test evidence. | PLAT-01; NFR-Observability
ECOM-072 | S10 | Delivery | Implement production deployment and rollback pipeline | Configure protected production promotion, migrations, smoke tests, deployment health checks and rollback process. | Release can be deployed with documented steps; rollback rehearsal works; approvals and secrets are gated. | P0 | DevOps | 8 | None | Not Started | Refine with PM; add implementation subtasks and test evidence. | Release Gates; NFR-Resilience
ECOM-073 | S10 | Resilience | Test backups and restoration | Confirm automated backups/retention; restore into isolated environment; document RPO/RTO targets. | Restore produces usable application data; evidence and actual recovery time recorded. | P0 | Cloud / Data | 5 | None | Not Started | Refine with PM; add implementation subtasks and test evidence. | NFR-Recovery; NFR-Reliability
ECOM-074 | S11 | UAT | Execute business UAT and capture sign-off | Run scenarios with product, operations and support; log defects with severity and evidence. | All P0 scenarios passed; owner signs off or documents accepted known issues. | P0 | PM / QA | 8 | None | Not Started | Refine with PM; add implementation subtasks and test evidence. | NFR-Testing; Release Gates
ECOM-075 | S11 | Release | Rehearse production migration and cutover | Validate schema migration sequence, opening inventory import, product content load, cache/CDN invalidation and rollback. | Rehearsal completes within planned window; checksums/counts and rollback path verified. | P0 | DevOps / Data | 5 | None | Not Started | Refine with PM; add implementation subtasks and test evidence. | Release Gates; NFR-Resilience
ECOM-076 | S11 | Payments | Validate provider live-mode readiness | Confirm production account approvals, callback URLs, webhook secrets, refund capability and reconciliation process. | A controlled low-value live transaction/refund is verified if allowed by provider/business; evidence retained securely. | P0 | Backend / Finance Ops | 5 | None | Not Started | Refine with PM; add implementation subtasks and test evidence. | PAY-01; PAY-02; PAY-04
ECOM-077 | S11 | Operations | Finalize support runbooks and escalation map | Document order/payment issue triage, refund steps, inventory correction, incident communications and escalation ownership. | Support staff complete walkthrough; no manual procedure requires direct DB editing for routine operations. | P0 | Ops / PM | 5 | None | Not Started | Refine with PM; add implementation subtasks and test evidence. | PRD review / cross-cutting
ECOM-078 | S11 | Analytics | Verify product and funnel analytics | Validate product view, search, add-to-cart, checkout start, payment result, purchase and refund events. | Events fire once per intended action; no payment details/PII in analytics payload; dashboards validated. | P1 | Data / Frontend | 5 | None | Not Started | Refine with PM; add implementation subtasks and test evidence. | ANA-01; ANA-02
ECOM-079 | S11 | Release | Conduct go/no-go review and release approval | Review release gates, open issues, monitoring, traffic plan, content, support, rollback and stakeholders. | Named approvers record go/no-go; launch owner and incident commander assigned. | P0 | PM / Engineering Lead | 3 | None | Not Started | Refine with PM; add implementation subtasks and test evidence. | Release Gates; NFR-Resilience
ECOM-080 | R | Launch | Deploy approved production release | Promote signed candidate using controlled rollout and observe core service health. | Deployment version recorded; smoke tests pass; rollback remains available. | P0 | DevOps / Engineering | 5 | None | Not Started | Refine with PM; add implementation subtasks and test evidence. | Release Gates; NFR-Resilience
ECOM-081 | R | Launch | Run production purchase smoke test | Place an agreed test order, verify payment event, order state, email, inventory decrement and refund/cancel as appropriate. | Order and payment reconcile end-to-end; test artifacts retained; no data leakage. | P0 | QA / Finance Ops | 3 | None | Not Started | Refine with PM; add implementation subtasks and test evidence. | Release Gates; NFR-Resilience
ECOM-082 | R | Launch | Monitor launch metrics and triage incidents | Monitor errors, latency, checkout conversion, payment failures, queue lag and support contacts during launch window. | Incident thresholds and response owners active; high-severity issues follow rollback/escalation playbook. | P0 | Engineering / Ops | 5 | None | Not Started | Refine with PM; add implementation subtasks and test evidence. | Release Gates; NFR-Resilience

## Risks & Decisions
RISKS, DEPENDENCIES & DECISIONS
Type | Item | Impact | Mitigation / Required action | Owner | Due
Decision | Launch market, currency, locale and tax display | Can block pricing, checkout, invoices, content and QA | Select market/currency; approve tax-inclusive/exclusive and address fields | PM / Finance / Legal | End S1
Decision | Payment provider and live account | Blocks checkout, webhook/refund behavior and launch smoke test | Choose provider; enable sandbox; confirm production onboarding and refund APIs | PM / Finance / Backend | End S1
Decision | Shipping coverage, cost and delivery estimates | Blocks checkout totals and delivery promises | Approve serviceable regions, shipping methods, rules, costs and tracking approach | PM / Operations | End S1
Decision | Cancellation / return / refund policy | Blocks S9 self-service workflows and state transitions | Define cutoff, window, exclusions, approval, restocking, partial refunds and timelines | PM / Operations / Finance | Before S9
Risk | Team capacity unknown | Scope and deadline may be unrealistic | Name owners and allocation; use S1–S2 velocity to reforecast; trim P1 before compromising gates | Engineering Lead / PM | End S1
Risk | Microservices over-fragmentation | Adds deployment and consistency overhead | Use bounded contexts first; split deployment only with a reason and owner | Architect | S1 ADR
Risk | Payment webhook duplication/order issues | Incorrect paid/refund state, duplicate email or inventory effects | Signed events, idempotency, event ledger, state machine, replay tests and reconciliation alerts | Backend / QA | S7
Risk | Inventory race conditions | Overselling and stranded reservations | Transactional reservations, expiry and concurrency tests | Backend | S6
Risk | Product data/content not ready | UAT/launch catalog incomplete | Assign owner, validate import format, define content freeze date and image rights | Product / Content | S3
Risk | Holiday capacity reduced | Cart/pricing work may slip | Explicitly reduce S5 capacity; avoid scheduling external approvals then | PM / Engineering Lead | S4 planning
Risk | Security findings late in schedule | Launch delay or unsafe go-live | Threat model S1; scan continuously; hardening S10; no unresolved high/critical findings without sign-off | Security / Engineering | All sprints
Risk | Operational readiness overlooked | Slow response to incidents/payments/refunds | Alerting, runbooks, backup restore, cutover and rollback rehearsals by S11 | Ops / DevOps | S11

## Launch Checklist
PRODUCTION LAUNCH CHECKLIST
ID | Gate | Pass criteria | Owner role | Status
G-01 | P0 scope accepted | All P0 requirements implemented and signed off; P1 either complete or deferred | Product Owner / PM | Not Started
G-02 | Purchase journey | Browse to order success and decline/cancel/retry paths pass in prod-like env | QA / Engineering | Not Started
G-03 | Payment integrity | Signed webhook, idempotency, refund and reconciliation scenarios have evidence | Backend / Finance Ops | Not Started
G-04 | Critical defects | Zero open Sev-1/Sev-2 defects | Engineering / QA | Not Started
G-05 | Security | No unresolved critical/high issue without formal risk acceptance | Security / Engineering Lead | Not Started
G-06 | Performance | Agreed traffic profile test passes and results are recorded | QA / Backend | Not Started
G-07 | Accessibility / SEO | Core journey accessibility review and technical SEO crawl pass | Frontend / QA / SEO | Not Started
G-08 | Data/content | Product catalog, stock and policy/legal content approved and loaded | Product / Operations | Not Started
G-09 | Observability | Dashboards, alert routing, correlation IDs and on-call ownership active | DevOps / Backend | Not Started
G-10 | Backup/recovery | Automated backup and restore rehearsal completed; RPO/RTO approved | Cloud / Data | Not Started
G-11 | Cutover/rollback | Production deploy, migrations, smoke test and rollback rehearsed | DevOps / Engineering | Not Started
G-12 | Provider production | Live credentials, callback URLs, webhook secrets and refund capability verified | Backend / Finance Ops | Not Started
G-13 | Support readiness | Support trained on lookup, fulfilment, inventory correction, refund and incident steps | Operations / Support | Not Started
G-14 | Go/no-go | Named approvers record decision; launch owner/incident commander assigned | PM / Business Owner | Not Started
G-15 | Production smoke test | Test order reconciles across payment/order/email/inventory; no critical incident | QA / Finance Ops | Not Started

## Read Me
HOW TO USE THIS PLAN
Artifact purpose | PM-ready starting baseline for roadmap, ticket breakdown and launch control. It is not a guarantee independent of team capacity.
Priority P0 | Must ship to meet agreed launch scope and safe production operation.
Priority P1 | Should ship if capacity remains after P0, security and release gates; defer formally if needed.
Priority P2 | Post-launch / explicitly excluded unless approved via change control.
Story points | Initial relative estimates only; re-estimate with the actual team in Sprint 1.
Status | Use dropdown in Ticket Backlog; add sub-tasks, assignees and test links in the team's delivery tool.
Dates | S1 starts 26 Oct 2026; production launch deadline is 31 Mar 2027. S5 has reduced holiday capacity.
Single-store assumption | Seller marketplace, seller payouts, native mobile apps and advanced loyalty are outside launch unless formally added.
Architecture note | Clear bounded contexts are required; each context does not automatically need a separate deployable microservice.
Use with PRD | Use Ecommerce_Website_PRD.docx / .md for requirements and acceptance conventions; keep sprint ticket rows linked to requirement IDs during refinement.

## Dashboard
ECOMMERCE WEBSITE — DELIVERY DASHBOARD
Metric | Value
Total ticket candidates | 82
P0 launch tickets | 75
P1 optional tickets | 7
Sprints incl. launch window | 12
Sprint | Sprint name | Ticket count | Story points
S1 | Discovery & Foundations | 10 | 39
S2 | Platform Shell & Identity | 9 | 44
S3 | Catalog & Discovery | 7 | 39
S4 | Product Detail & Inventory | 6 | 34
S5 | Cart, Wishlist & Offers | 6 | 34
S6 | Checkout & Payment Integration | 7 | 44
S7 | Orders & Payment Reconciliation | 6 | 39
S8 | Admin & Operations | 7 | 41
S9 | Retention, Reviews & Self-Service | 7 | 45
S10 | System Hardening & Release Candidate | 8 | 55
S11 | UAT, Cutover & Launch Readiness | 6 | 31
R | Production Launch Window | 3 | 13